## WeekMar25
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
create web interface | Nisa | 4 | 2023-02-17
Research flask app | Adrian | 3 | 2023-02-17
Research mechanics | Josh | 3 | 2023-02-17